## Sheet1
ID | Classification | Cause | Qualitive Impact | Quantitive Impact | Prevention Strategy
1 | Project | Time Management | Severe | 5+ days | Each week I will make sure to follow the "Time-Box" methodology, avoiding failing any sprints.
2 | Health | Stress | Severe | 5+ days | Need to ensure to get the apropriate amount of sleep necessary, using breathing exercises and do some regular exercise.
3 | Project | Project becomes lost or damaged | Medium | 5+ days | Having always a backup for the project at GitHub and google drive.
4 | Health | Repetitive Strain Injury | Minor | 10 days | Ensure regular breaks are taken. For this I implement the pomodoro techinique, each 25 minutes of work, you take a break of 5 minutes.
5 | Social | Death in the family | Severe | 20+ days | N/A
6 | Health | Health Problems | Minor | 2 days | Eat healthy, Exercise, Take medication
7 | Health | Natural catstrophe | Critical | Entire Project | N/A
8 | Project | Missing sprint deadline | Medium | 4 days | Making sure to dedicated enough time for each sprint, if the time dedicated for the sprint is not enough, increase the work load to avoid missing the deadline
9 | Project | Failure in feature implementation | Severe | 5+ days | Make sure to research enough to avoid failing in implementing features. If the feature provides to be to dificult to implement, search for alternative ways to achieve the same result
10 | Project | Insufficient Testing | Severe | 5+ days | Testing the program at the end of each sprint is something that is usualy neglted. Make sure that at the end of each sprint, the code is tested and is working correctly