## Slide 1: Final Major Project
Computer Games SD
Computer Games Indie

## Slide 2: FMP Overview
Project Handbook
Supervisors
Project Topics
Project vs product
Reports
Project Management
Phases & key dates

## Slide 3: What is the FMP?
The Final Major Project your big opportunity to show the knowledge and skills gained over 3 years
Research, plan and develop a product appropriate for your course
Independent work with guidance from your project supervisor
40 CATS points - double value unit!
4 written reports
  2 of them are summatively assessed
Demonstration
Grad Show

## Slide 4: What is the FMP?
"Develop and extend" knowledge and skills obtained on the course
You cannot simply choose to make a game
  Requires too much effort in non-course related areas
  But it can be done…*
SD - software emphasis
  Technical solutions / System
  Tool / Plugin / Middleware
  Prototype / Proof-of-Concept
Indie - marketable product
  Business case
  Documented product

## Slide 5: Project Phases
Identification
Question & Topic
Aims
Proposal
Research
Background
Existing research
Potential solutions
Selection
Tools/methods
Process
Planning
Dependencies
Risks
Determination
Specification
Progress Report
Implementation
Execute & Monitor
Change control
Product
Review
Final Report
Demonstration
Grad Show
Definition Report
Aims & Objectives
Notes: Identification of a problem to be solved followed by formal definition in terms of aims and measurable objectives.
Research into potential solutions to the given problem, and criteria-based selection of potential solution(s).
Selection of suitable tools/methods to be used in the process of solving the problem.
Planning the process of solving the problem, including contingency and risk analysis.
Determination of methods whereby the success or otherwise of all aspects of the project can be assessed.
Implementation of a product or primary research results and analysis.
Review and reporting on the product and the process.

## Slide 6: Project Documents
Project Proposal
Definition Report
Progress Report
Set initial direction
Complete description
Aims and Objectives
Initial plan
Research results
Final Report
Implementation plan
Discussion of implementation
Analysis and conclusions of project
1-2 pages
5+ pages
10+ pages
20+ pages
Each report builds on the previous
Everything contributes to the Final Report

## Slide 7: Product and Project
The Product is what you build…
  Gameplay prototype
  Technical demo
  Branching narrative system
  Unity Plugin
  Unreal mod
The Project is your approach and methods used in building the product
  Planning
  Decision making
  Identifying and managing risks
  Estimating time
  Managing changes
Your Grade
Your Portfolio

## Slide 8: Supervisors
Primary supervisor
  Main source of information
  Ideally have some experience with your Topic
  Weekly meetings in P2
  Provides guidance and suggestions
  Formative feedback
Primary and Secondary supervisor
  Approve Proposal and Topic
  Mark Reports
  Review demonstration

## Slide 9: Project Management
Project management can be very time consuming and challenging
Many students struggle to find an appropriate methodology
Many students struggle to follow their chosen methodology (esp. Agile)
Many students score poorly in project management criteria
We strongly recommend using a hybrid Prescriptive Framework based on weekly a "timebox"

## Slide 10: "Timeboxed" Development
Timebox
Fixed duration "mini-project"
Focused set of goals/theme
Avoid work carrying over
  Reduce scope instead
Same principle as an agile Sprint
Review
Do
Plan

## Slide 11: Work Breakdown Structure (WBS)
Hierarchical decomposition of project scope into one or more levels of smaller components
  100% rule
  No overlap
  Coding scheme
Break down big goals/User Stories into increasingly smaller pieces
Tasks are the smallest element
  Feature
  Component
  Discipline/skill: Design, Programming, Audio, Art …
  1 Feature1
      1.1 Component 1
      1.1.1 Task 1
      1.2 Component 2
      1.2.1 Task 1
      1.2.2 Task 2
  Feature 2
      2.1 Component 1
      1.2.1 Task 1
      1.2.2 Task 2
      1.2.3 Task 3
  Feature 3…

## Slide 12: Gantt
https://commons.wikimedia.org/w/index.php?curid=15018988
Visual summary
Task sequencing
Subtasks
Dependencies
Progress

## Slide 13: "Timeboxed" Development
Timebox 1
Review
Do
Plan
WBS
Gantt
Timebox 2
Review
Do
Plan
WBS 2
Gantt 2
Tracking
Tracking 2

## Slide 14: All activities can be Timeboxed
Coding
Final
Progress
Thinking
Research
Definition
Recording notes
Prototyping
Planning
Analysing
Experiment
Research
Organising
Writing
Managing

## Slide 15: Important Dates
Next L6 Meeting 22nd-Jan
Project Proposal w/c 25th-Jan
Definition Report w/c 12th-Feb
Progress Report 1st-Mar
Mid-point Prototype w/c 1st-Apr
Final Product and Report 3rd-May
Grad Show 22nd-May ?

## Slide 16: Questions?